## 📊 Gantt Chart
PROJECT GANTT CHART
Edit the Task Data below. The chart bars update automatically via conditional formatting.
# | Task / Milestone | Owner | Status | Start Date | End Date | Duration (days) | % Done | June 2026 | [22 empty] | July 2026 | [30 empty] | August 2026
[8 empty] | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6
PHASE 1 — PLANNING
★ | Project Kickoff | Alice | Done | 2026-06-08 | 2026-06-08 | 0 | 100% | bar: June 2026 8
2 | Requirements Gathering | Alice | Done | 2026-06-09 | 2026-06-13 | 5 | 100% | bar: June 2026 9 to June 2026 13
3 | Stakeholder Sign-off | Bob | Done | 2026-06-14 | 2026-06-15 | 2 | 100% | bar: June 2026 14 to June 2026 15
PHASE 2 — DESIGN
4 | Wireframes | Carol | Done | 2026-06-16 | 2026-06-19 | 4 | 100% | bar: June 2026 16 to June 2026 19
5 | UI Design | Carol | In Progress | 2026-06-20 | 2026-06-25 | 6 | 60% | bar: June 2026 20 to June 2026 25
6 | Design Review | Bob | In Progress | 2026-06-26 | 2026-06-27 | 2 | 30% | bar: June 2026 26 to June 2026 27
PHASE 3 — DEVELOPMENT
7 | Backend Setup | Dave | In Progress | 2026-06-23 | 2026-06-30 | 8 | 50% | bar: June 2026 23 to June 2026 30
8 | Frontend Development | Eve | Not Started | 2026-06-28 | 2026-07-07 | 10 | 0% | bar: June 2026 28 to July 2026 7
9 | API Integration | Dave | Not Started | 2026-07-06 | 2026-07-11 | 6 | 0% | bar: July 2026 6 to July 2026 11
10 | Unit Testing | Frank | Not Started | 2026-07-10 | 2026-07-14 | 5 | 0% | bar: July 2026 10 to July 2026 14
PHASE 4 — LAUNCH
11 | UAT | Alice | Not Started | 2026-07-15 | 2026-07-18 | 4 | 0% | bar: July 2026 15 to July 2026 18
12 | Bug Fixes | Dave | Not Started | 2026-07-19 | 2026-07-21 | 3 | 0% | bar: July 2026 19 to July 2026 21
★ | Go-Live 🚀 | Bob | Not Started | 2026-07-22 | 2026-07-22 | 0 | 0% | bar: July 2026 22
14 | Post-Launch Review | Alice | Not Started | 2026-07-24 | 2026-07-26 | 3 | 0% | bar: July 2026 24 to July 2026 26

## 📖 How To Use
📖 HOW TO USE THIS GANTT CHART
🚀 QUICK START (3 steps)
1️⃣ Go to the '📊 Gantt Chart' tab.
2️⃣ Edit columns A–H (task name, owner, status, start date, end date, % done). The Gantt bars will update automatically.
3️⃣ Add or delete rows inside the task list as needed. Keep the row format consistent.
📋 UNDERSTANDING THE COLUMNS
# (Col A) — Auto number or ★ for milestones. Update manually if you add rows.
Task / Milestone (Col B) — Enter your task name. Phase headers are pre-styled in dark blue.
Owner (Col C) — Person responsible for the task.
Status (Col D) — Choose: Done ¦ In Progress ¦ Not Started ¦ On Hold ¦ Delayed
Start Date (Col E)— Enter the task start date in any date format Excel recognises.
End Date (Col F) — Enter the task end date. Must be ≥ Start Date.
Duration (Col G) — Calculated automatically from Start and End dates. Do not edit.
% Done (Col H) — Enter a value 0–100. Formatted as a percentage automatically.
🎨 COLOUR LEGEND
🟦 Blue bar — Task 'In Progress'
🟩 Green bar — Task 'Done' (100 % complete)
🔵 Light Blue bar — Task 'Not Started'
🟠 Orange bar — Task 'On Hold'
🔴 Red bar — Task 'Delayed'
◆ Amber diamond — Milestone marker
🔴 Red date header— Today's date
⬜ Grey columns — Weekend days
➕ ADDING A NEW TASK
1. Click on a row inside the task list.
2. Right-click → Insert Row.
3. Copy the formatting from an adjacent row (Home → Paste Special → Formats).
4. Fill in columns A–H with your task data.
5. The Gantt bar cells in that row are plain cells coloured by the start/end dates — you must copy the fill colour logic from a neighbouring row or re-enter the bar manually for now (full conditional formatting requires Excel macros).
🗓️ CHANGING THE DATE RANGE
The date columns start from the Monday of the week when this file was created.
To shift the start date: a developer can update the 'project_start' variable in the Python script and regenerate.
Alternatively, manually change the date numbers in Row 4 (the date header row) and re-colour the bar cells.
💡 TIPS & BEST PRACTICES
• Freeze panes are already set at column E / row 5 so task names stay visible while you scroll right.
• Keep phase/section rows (dark blue, all-caps) as separators — do not put dates in them.
• Use the Status column consistently; it drives the bar colour.
• Print: use Landscape orientation, 'Fit to 1 page wide' in Page Layout → Scale to Fit.
• Save a backup before making large structural changes.
• For recurring use, clear columns E–H and update dates each sprint/project cycle.

## 🎨 Legend
STATUS & COLOUR LEGEND
Status | Bar Colour
Done | Green #70AD47
In Progress | Blue #2E75B6
Not Started | Lt Blue #9DC3E6
On Hold | Orange #FF9900
Delayed | Red #FF0000
Milestone ★ | Amber #FFF2CC
Weekend | Grey #D6DCE4
Today | Red #FF0000